**Duration Estimate  
Gant Chart**

**Team 1**

**St. Charles Community College**

**4601 Mid Rivers Mall Drive**

**Cottleville, MO**

**63376**

**Date**

**March 1, 2025**

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Durations Estimate** | | | | | | | |
| **Project:** PlanAI | | | | | **Date:** 03/01/2025 | | |
| **Activity** | **Resource(s)** | **Optimistic** | **Most Likely** | **Pessimistic** | **Estimated Activity Duration** | **Reserve** | |
| Add members to repo | Instructions from module on how to do it | 1 day | 1 day | 2 days | 1-1 ½ days | | 1 day |
| Decide on project idea | Google, Team members | 3 days | 3 days | 6 days | 3 days | | 1 day |
| Install software needed | Google,  YouTube,  Team members | 5 days | 7 days | 10 days | 7 days | | 1 day |
| Finish phase 1 documents  /turn in | Team members | 5 days | 5 days | 7 days | 5 days | | 2 days |
| Complete PowerPoint | Team members | 7 days | 12 days | 13 days | 7 days | | 1 day |
| Design/  implement GUI | Team members, w3schools website | 14 days | 14 days | 21 days | 15 days | | 7 days |
| Start design of database | Team members, YouTube | 14 days | 14 days | 21 days | 15 days | | 7 days |
| Add Google login API | Team members,  class lectures | 2 days | 4 days | 7 days | 4 days | | 2 days |
| Complete PowerPoint/  turn in finished work | Team members | 2 days | 5 days | 7 days | 3 days | | 2 days |
| Finish & turn in phase 3 work | Team members | 14 days | 18 days | 21 days | 15 days | | 7 days |
| Finish & turn in phase 4 work | Team member | 3 days | 3 days | 6 days | 3 days | | 1 day |
| Finalize & turn in finished project | Team members | 3 days | 4 days | 6 days | 5 days | | 2 days |

This free Duration Estimate Template is brought to you by [www.ProjectManagementDocs.com](http://www.ProjectManagementDocs.com)